# Plant Bus Commissioning Action Plan for Regulated Manufacturing

## Executive summary

You can’t “commission an event bus” in a regulated area without business-owned events, contracts, and validation gates. The broker and integration stack (Ignition + HighByte Intelligence Hub + HiveMQ) is necessary infrastructure, but it only produces value when directors define (and sign) the MVP use cases, the domain events that drive those use cases, and the data integrity / record-impact boundaries that determine validation rigor. FDA’s CGMP data integrity guidance defines data integrity as completeness/consistency/accuracy and explicitly ties it to ALCOA and required metadata (e.g., timestamp, user ID, instrument ID, units); those expectations apply across creation through transmission and retention. [1] In parallel, 21 CFR 11.10 requires secure, computer-generated, time-stamped audit trails for electronic records (when Part 11 applies) and requires record changes not obscure prior information. [2] ISPE’s GAMP framework is explicitly oriented to ensuring computerized systems are fit for intended use and compliant. [3]

On the technology side: Ignition’s IIoT architecture describes publishing edge/field data to a central MQTT broker (e.g., via MQTT Transmission / Edge MQTT) and subscribing consumers via MQTT Engine. [4] HighByte’s MQTT connection explicitly supports connecting to MQTT brokers to read/write messages and includes configuration for redundant brokers. [5] HiveMQ’s documentation explicitly covers broker security (TLS, authentication/authorization capabilities) and cluster replication of persisted data across nodes for resilience. [6]

## Assumptions

Regulatory context is assumed to be GxP with data integrity expectations aligned to FDA CGMP guidance (ALCOA) and potential Part 11 applicability, but your exact applicable regulations, product types, and inspection expectations are not specified; this plan therefore uses risk-based gates and requires Quality to classify “record impact” per use case. [7]

Unspecified items that must be treated as assumptions until directors decide: - Exact versions/licensing of Ignition modules and deployed patterns (central vs edge); the provided plan aligns to Ignition’s published IIoT/MQTT architecture description. [4]
- Broker topology (single node vs cluster/HA), identity provider, network segmentation model, and whether events are evidence for batch release or other regulated decisions (record impact). [8]
- Whether Sparkplug-style state management is used; if so, Sparkplug’s STATE/BIRTH sequencing requirements become operationally relevant for availability/health semantics. [9]

## Director actions now

| VP Sponsor | Manufacturing Director | Quality Director | Automation/Controls Director | IT/OT Infrastructure Director | MES/MOM Director | QC/Lab Director |
| --- | --- | --- | --- | --- | --- | --- |
| Sign Plant Bus charter + funding and name Design Authority chair | Approve MVP use cases + name process SMEs with weekly hours committed | Classify each MVP use case as record-impact vs informational; approve validation evidence expectations | Confirm event producers (equipment/PLC/SCADA sources) + ownership for signal meaning | Commit broker SLA, security baseline (TLS/authz), monitoring + on-call model | Confirm system-of-record boundaries (MES vs bus) + consumer readiness | Define lab/instrument event states (result available/approved/rejected) + metadata needed for integrity |

Non-optional inputs required from directors (no input = no commissioning): - MVP use-case titles and priority order for the new area (5–10 max for go-live).
- For each MVP use case: record-impact classification (electronic record vs informational telemetry) and system-of-record decision. [10]
- Event ownership assignments: one business owner (meaning) and one technical owner (producer pipeline) per event.
- Metadata minimums per event type (timestamp source, user identity expectations, instrument/equipment identifiers, units, etc.), aligned to data integrity expectations. [1]
- Security decisions: who may publish/subscribe by topic class; TLS requirement; identity integration plan (broker authorization approach). HiveMQ documents TLS and authn/authz capabilities and expects deliberate configuration choices. [11]
- Operations/SLA targets (uptime, recovery time, latency expectations) and the on-call model for broker, modeling/pipelines, and edge connectivity; broker monitoring is explicitly recommended as a production requirement. [12]
- Validation approach proportional to risk (“fit for intended use”) and evidence deliverables for go/no-go gates. [3]

## Recipe for success

1) Establish governance and decision rights
Owner role: VP Sponsor
Deliverable: Signed charter naming Design Authority members, decision rights, funding, and “what success looks like” (KPIs + SLA targets)
Timebox: Week 1
Go/No-Go gate: No technical commissioning beyond connectivity until charter + authority are signed (GAMP principle: intended use drives scope). [3]

2) Define MVP outcomes and use-case portfolio
Owner role: Manufacturing Director (co-sign: MES Director, QC/Lab Director, Quality Director)
Deliverable: Ranked MVP use-case list + 1–2 sentence “intended use” per use case and initial KPIs
Timebox: Week 1–2
Go/No-Go gate: At least 5 MVP use cases approved with a single accountable director per use case (no owner = no build)

3) Classify record impact and data integrity requirements per use case
Owner role: Quality Director
Deliverable: For each MVP use case: record-impact classification, required metadata, audit trail expectations, retention expectations, and validation evidence level
Timebox: Week 2
Go/No-Go gate: “Record-impact” use cases must have written metadata + audit trail + retention expectations consistent with FDA data integrity guidance and Part 11 controls where applicable. [7]

4) Run event discovery and lock the event catalog
Owner role: Manufacturing Director (facilitated by Plant Bus architect; Quality participates)
Deliverable: Event Catalog v1 (event names, definitions, producer, consumers, criticality, frequency/latency, owner, record-impact flag)
Timebox: Week 2–3
Go/No-Go gate: Catalog is signed by Manufacturing + Quality; events without definitions/owners do not ship

5) Standardize namespace and contracts before building
Owner role: IT/OT Infrastructure Director (co-sign: Automation Director + Quality Director for record-impact topics)
Deliverable: Topic hierarchy standard + versioning rules + minimum contract fields (template below)
Timebox: Week 3
Go/No-Go gate: First consumer build cannot start until contract template and versioning rules are approved (prevents “tribal JSON” integrations)

6) Commission broker security, resilience, and observability baseline
Owner role: IT/OT Infrastructure Director
Deliverable: HiveMQ baseline: TLS enabled, authn/authz approach selected, monitoring dashboards and alerting, backup/restore plan, HA/clustering decision
Timebox: Week 3–4
Go/No-Go gate: No production publishing until TLS/authz and monitoring are in place; HiveMQ documents TLS configuration and emphasizes deliberate security/monitoring in critical deployments. [13]
(If HA/cluster is required, HiveMQ cluster replication behavior must be validated for your SLA.) [14]

7) Commission producers and pipelines for MVP events
Owner role: Automation/Controls Director (OT sources) + Plant Bus integration lead
Deliverable: Ignition/edge sources publishing defined events to broker; HighByte pipelines/modeling producing standardized payloads where needed
Timebox: Weeks 4–7
Go/No-Go gate: Each MVP event must pass: (a) contract validation, (b) required metadata present, (c) producer health check, (d) topic authorization verified
Support basis: Ignition’s IIoT architecture explicitly supports publishing to a broker and subscribing applications. [4] HighByte MQTT connection supports broker read/write and redundant broker configuration. [5] HighByte modeling combines multiple source systems into standardized information for upstream consumers. [15]

8) Commission consumers and workflows for MVP use cases
Owner role: MES/MOM Director (MES workflows) and QC/Lab Director (instrument workflows)
Deliverable: Consumer subscriptions + workflow actions + user-facing procedures (including review-by-exception where applicable)
Timebox: Weeks 6–9
Go/No-Go gate: Each MVP use case meets acceptance criteria, including data integrity checks (metadata completeness, units, traceability) consistent with FDA guidance. [1]

9) Execute performance, failure-mode, and recovery testing
Owner role: IT/OT Infrastructure Director (broker) + Quality Director (evidence acceptance)
Deliverable: Test evidence for latency, throughput, reconnect behavior, message persistence expectations, and recovery; documented incident playbooks
Timebox: Week 10
Go/No-Go gate: SLA tests pass and recovery procedures are proven; cluster replication behavior must meet your durability expectations if clustering is used. [16]

10) Go-live readiness review and operations handoff
Owner role: VP Sponsor (chair), with Manufacturing + Quality sign-off
Deliverable: Go-live package: signed intended use, event catalog, contracts, security baseline, monitoring, training completion, and validation evidence appropriate to risk (“fit for intended use”)
Timebox: Weeks 11–12
Go/No-Go gate: Quality approves record-impact use cases for release; Part 11 audit trail expectations are demonstrably met where applicable. [17]

## MVP use cases

Prioritized MVP use cases (titles only): - Batch Started / Batch Completed event-to-MES synchronization
- Material Weighing Completed with automatic record population
- Equipment Hold Applied / Hold Released with reason codes
- Sample Collected with chain-of-custody metadata
- Analytical Result Available (raw)
- Analytical Result Approved / Result Rejected (quality state change)
- Critical Process Exception Detected (OOE/OOS trigger event)
- Manual transcription elimination for defined critical readings at defined steps

## Minimum event contract

Minimum event contract template (fields only): - event_id
- event_type
- event_version
- occurred_at_utc
- produced_at_utc
- site
- area
- line_or_cell
- asset_id
- asset_type
- source_system
- producer_instance_id
- batch_id
- lot_id
- work_order_id
- material_id
- material_status
- sample_id
- test_id
- instrument_id
- user_id
- unit_of_measure
- value
- value_type
- quality_code
- reason_code
- comment
- correlation_id
- causation_id
- data_classification (e.g., gxp_record_impact yes/no)
- audit_trail_ref (system-of-record pointer)
- retention_class
- checksum_or_hash (if used)

(These fields intentionally align to FDA guidance emphasis that meaningful CGMP data requires metadata such as timestamps, user ID, instrument ID, units, status, and audit trail associations. [1])

## KPIs and operating targets

Top 5 KPIs to measure Plant Bus commissioning success: - MVP adoption: % of targeted shifts/batches using Plant Bus-backed workflows (per use case)
- Transcription elimination: count of eliminated manual entries (or hours saved) tied to the MVP use cases
- End-to-end event latency: p95 time from occurred_at to consumer action (per critical event type)
- Contract compliance: % of events meeting required metadata completeness (ALCOA/traceability fields present) [1]
- Platform reliability: broker availability + MTTR + number of severity-1 integration incidents; HiveMQ explicitly positions monitoring as essential in production, especially clustered environments [12]

## Twelve-week commissioning plan

gantt
    title Plant Bus commissioning (12 weeks)
    dateFormat  YYYY-MM-DD
    axisFormat  %b %d

    section Governance & requirements
    Charter + Design Authority (Step 1)           :a1, 2026-03-09, 5d
    MVP use cases + intended use (Step 2)         :a2, 2026-03-09, 10d
    Record-impact + integrity classification (3)  :a3, 2026-03-16, 5d
    Event catalog workshop + sign-off (4)         :a4, 2026-03-16, 10d
    Namespace + contract standards (5)            :a5, 2026-03-23, 5d

    section Platform baseline
    HiveMQ security/monitoring/HA decision (6)    :b1, 2026-03-23, 10d

    section Build & commission
    Producers + HighByte modeling/pipelines (7)   :c1, 2026-03-30, 20d
    Consumers + workflows + SOP updates (8)       :c2, 2026-04-13, 20d

    section Evidence & release
    Performance/failure/recovery testing (9)      :d1, 2026-05-18, 5d
    Go-live readiness + training + handoff (10)   :d2, 2026-05-25, 10d

[1] [7] Guidance for Industry

https://www.fda.gov/media/119267/download

[2] [10]  eCFR :: 21 CFR 11.10 -- Controls for closed systems.

https://www.ecfr.gov/current/title-21/chapter-I/subchapter-A/part-11/subpart-B/section-11.10

[3] [17] GAMP 5 Guide 2nd Edition | ISPE | International Society for Pharmaceutical Engineering

https://ispe.org/publications/guidance-documents/gamp-5-guide-2nd-edition

[4] IIoT Architecture | Ignition User Manual

https://www.docs.inductiveautomation.com/docs/7.9/getting-started/system-architectures/iiot-architecture

[5] MQTT | User Guide

https://guide.highbyte.com/configuration/connect/connections/mqtt/

[6] [11] [13] Security Features of HiveMQ :: HiveMQ Documentation

https://docs.hivemq.com/hivemq/latest/user-guide/security.html

[8] [14] [16] HiveMQ MQTT Broker Clusters :: HiveMQ Documentation

https://docs.hivemq.com/hivemq/latest/user-guide/cluster.html

[9] Sparkplug 3.0.0: Sparkplug Specification

https://sparkplug.eclipse.org/specification/version/3.0/documents/sparkplug-specification-3.0.0.pdf

[12] Monitoring :: HiveMQ Documentation

https://docs.hivemq.com/hivemq/latest/user-guide/monitoring.html

[15] Model | User Guide

https://guide.highbyte.com/configuration/model/